## Change Impact Entry
Use this Change Management Assessment Template to track organizational changes, document their progress, flag the stakeholders impacted, and analyze the risks, benefits, and mitigation factors associated with each change element. Hover over each title cell to see instructions for filling in the template.
Last Updated:
Stakeholders Affected
ID | Change Impact Area | Functional Area Impact | Change Impact | Current State Overview | Internal Staff Affected? | Stakeholder A | Stakeholder B | Stakeholder C | Level of Impact | Anticipated Risks / Challenges | Potential Benefits | Mitigation | Notes
| Combining two programs | Operations, programming, human resources, technology, strategy, marketing | Combining the programs will help us focus staff capacity on the services that further our organizational and strategic goals. Program change also means that some staff will have to adjust to new roles, responsibilities, and assignments. | Leadership team plans to announce program change at the staff meeting on 5/17/2019. | Direct services staff Development team | X | X |  | Significant | Staff buy-in will require work to ensure; marketing team will have to create new collateral to market our services; challenge to spread new messaging of services to the local community. | Staff will ultimately have more time to focus directly on the populations we serve in order to amplify our mission and meet strategic goals. | Create regular check-ins with managers and anonymous feedback structure so that direct services staff can share their questions, concerns, and points of feedback openly with senior leadership.
Note on B6: Use a number ID system to organize the various pieces of organizational change happening.
Note on C6: What is the change that is happening?
Note on D6: Which functional area of your organization's operations is affected by this change (i.e technology, programming, marketing, etc.)
Note on E6: What are the benefits or concerns of the change? What will happen as a result of this change?
Note on F6: What is the current status of the change? Note here whether the change has been announced and what stage of its implementation life cycle it's in.
Note on G6: Who are the main individuals, groups, or departments affected by this change?
Note on H5: Leave space for your organization's stakeholders here and mark whether or not they are affected by this change.
Note on K6: How deeply will this change affect the stakeholders you listed to the left? Is this an organization-wide change or specific to a department?
Note on L6: What do you anticipate are the major risks and challenges of this change?
Note on M6: Why will this change result in a positive outcome for your organization?
Note on N6: What is the plan for mitigating the risks you listed to the left in order to amplify the potential benefits?